Project overview:

This 2-3 months Human-Centred Design (HCD) project will explore how Early-Mid adolescents (secondary school youths) wish to be engaged, and what would trigger and support them in sustaining healthy habits while understanding how parents can be better supported to effectively engage and support their child.

Target audience:

| Primary | Early-Mid adolescents (Secondary school youths), including those at transitional ages (i.e. 12 to 13 years old and 16 to 17 years old) and their parents/caregivers |
| --- | --- |
| Secondary (where appropriate) | E.g. Schools, Educators, Community Partners |

Business objectives/KPIs:

| Primary | Develop tried and tested, Desirability-Viability-Feasibility (DVF) -assessed prototypes for HPB’s internal pilot testing with 30 youths (across age bands) and 10 parents from Jan – March 2026 |
| --- | --- |
| Secondary | Further our understanding of our target audience (within the 0-18 continuum) by addressing knowledge gaps in early-mid adolescence and key transition points (i.e. Pri 6 to Sec 1, Sec 2 to Sec 3, Sec 4 to JC/ IHLs). Areas to further deep dive in this HCD: - Priorities, behaviours, influences of early-mid adolescence to inform the approaches and design for secondary school lifestyle interventions - Parent-youth dynamics to generate actionable insights for appropriate parental support as youth navigate transitions - Key transition periods where habits undergo significant shifts to inform the approach and design for supporting parents and youth in these critical stages - Resource preferences and engagement within school environments (list of existing HPB resources and engagements will be shared when awarded) to inform the design and implementation of effective health resources post health plan (for students) - Student-driven activity preferences and intrinsic motivators to inform the development of engaging in-school and out-of-school health and wellness programmes - Non-digital resource effectiveness and accessibility to inform the design of alternative and complementary approaches to health interventions |

ANNEX A: Project Background

Children and youth in Singapore face rising health risks from inactivity, poor diet, excessive screen use, inadequate sleep, and declining oral health. Early intervention is critical to build lasting habits.

Grow Well SG (GWSG) jointly led by MOH, MOE, and MSF, integrates school, family and community touchpoints to promote five behaviours: eat well, exercise well, sleep well, learn well (screen use), and oral health. Through school health screening, HPB provides every child with a personalised Health Plan, aligned with the HealthierSG approach.

GWSG works alongside educators, healthcare professionals, and community partners to nurture a generation of children who are active, sociable, well-nourished and rested, and capable of engaging with technology in healthy and productive ways, through family bonds and friendship.

Having launched with younger children aged 6 to 8 in 2025, GWSG is now expanding to youths (13–18). This stage is critical: screen use averages 8.5 hours daily, impacting sleep and physical activity, while oral health worsens with increased caries risk between age 12 to 15. These behaviour changes do not occur in isolation – patterns in one area often influence others – showing that the 5 behaviours are interconnected, with effects in one behaviour spilling over into the rest. Additionally, preliminary findings from past studies have shown that early-mid adolescents have general health awareness but there are influences that undermines them from practicing healthy behaviours. These influences (to be validated) include i) perceived invincibility, ii) competing personal goals, iii) knowledge gaps, iv) translation barriers (Refer to Annex C for more details).

As youths undergo developmental phases while navigating their increased desire for autonomy, parents’ roles shift and ecosystem influence strengthens, further shaping the development of these interconnected behaviours. Research have also pointed that youths crave for bonding despite seeking independence. On the other hand, parents make way for their child to navigate independence although their desire for quality time with their child remains. Findings have revealed that parents struggle to monitor and enforce healthy behaviours due to their limited knowledge on effective strategies in setting consistent routines, and it is important for both parents and youth to thread the parent-youth dynamics carefully.

Therefore, this highlights the need for a deeper understanding of both parents and youths’ perspective of each other and how to better support youths and their parents in cultivating healthier habits.

HPB’s customer experience ambition is to deliver holistic, intuitive, inspiring and personalised support that meets rising expectations shaped by both public and private sectors.

Focus areas (key gaps to explore):

- How might we improve youth health outcomes by anchoring solutions in their top-of-mind concerns rather than leading with health messaging?

- How might we better support youths in translating health knowledge into action? What are the barriers and ecosystem levers (including peers) to empower them?

- What parental support does youths/parents value particularly in key transition periods (i.e. Primary 6 to Secondary 1, and Secondary 2 to Secondary 3, Secondary 4 to Junior College or Institutes of Higher Learnings)?

- How might we empower parents to supportively guide rather than control their youths, fostering mutual connection during this critical developmental phase?

- How do family practices in earlier developmental stages impact youths’ receptivity to interventions in their later years (e.g. parent-induced stigma on negative connotations towards seeking help for mental health)?

- How might we design and deliver health resources within school environments that genuinely resonate with students and complement existing health plans? What formats and approaches maximise engagement and practical application?

- How might we tap into youths' intrinsic motivations and preferences to create meaningful health and wellness activities both within and beyond the school setting? What drives their authentic participation versus compliance?

- How might we leverage non-digital resources and approaches to create accessible, engaging alternatives that complement digital health interventions? When and why do youths prefer tangible, face-to-face, or hands-on support?

ANNEX B – Past findings to validate and build upon

- Early-mid adolescents have general health awareness but there are influences that undermines them from practicing healthy behaviours. This HCD study will seek to validate these influences:

- Perceived invincibility: Early-mid adolescents feel young and healthy now, hence they perceived risk of future health problems as low.

- Competing personal goals: physical appearances, academic pressure, career preparations, and social demands (e.g. peers) take precedence over long-term health.

- Knowledge gaps: Awareness exists among early-mid adolescents but specific knowledge is lacking (for e.g. minimum activity guidelines, proper oral care).

- Translation barriers: Early-mid adolescents’ inability to translate health knowledge into consistent daily behaviours and self-regulation. Especially in areas such as:

- Nutrition – shift from family-provided meals to eating out with poorer choices

- Sleep – resisting parental routines but lack confidence establishing new routines

- Parents’ role remains influential in shaping most early-mid adolescent’s health but their role evolves as their child grows. Emerging themes have shown that it is not parental involvement itself that is critical but the approach taken – with attuned, positive and supportive methods being the most impactful:

- Sensitive attunement: the ability to notice and respond to their child without being overly controlling, particularly at this age where the child has increasing desire for autonomy.

- Positive engagement: Engaging child through encouragement, role modelling and shared activities can help nudge early-mid adolescents towards positive health behaviours

- Monitoring & supervision: this can be supportive when clear and flexible boundaries are communicated upfront.

- Open communication: Foster safe, 2-way dialogues, enabling parent and child to listen and understand each other’s perspectives.

Additionally, studies have also shown that early-mid adolescents continues to crave bonding with parents while seeking independence. This presents an opportunity for parents to influence through meaningful connection with them. A commonality observed from both early-mid adolescents’ and parents’ perspective is to bond through shared activities.

- Early-mid adolescent’s perspective on parents:

- Perception on parental support can be both positive and negative. E.g. exercising together can be motivating or embarrassing

- However there are moments when early-mid adolescents look up to their parents and yearn for connection especially via shared activities. Therefore, this HCD study should look into what are the factors that help early-mid adolescents to open up and connect with their parents.

- Parent’s perspective on early-mid adolescents

- Parents make way for their child to navigate independence, however, their desire for quality time with their child remains. They struggle to monitor and enforce healthy behaviours due to their limited knowledge on effective strategies in setting consistent routines.

This HCD study should help to shed some light in understanding parents’ struggle on the “how-to” and how we can empower them in supporting their child through this developmental phase.